## Slide 1: SAP Greenfield Transformations
Successful execution of large-scale SAP transformations, including keys for success and best practices

## Slide 2: About Duke Energy & Piedmont Natural Gas
Duke Energy (NYSE: DUK), a Fortune 150 company headquartered in Charlotte, N.C., is one of America’s largest energy holding companies.
Piedmont Natural Gas is a subsidiary of Duke Energy and distributes natural gas to 1.2 million customers in North Carolina, South Carolina and Tennessee. Piedmont Natural Gas is routinely recognized by J.D. Power for excellent customer satisfaction, and has been named by Cogent Reports as one of the most trusted utility brands in the U.S.
8.6M
55k
7
Electric Customers
States Serviced
MW of Energy Capacity
# of Customers by State: | Electric | Gas
North Carolina | 3.8M | 817K1
South Carolina | 856K | 169K1
Ohio/Kentucky | 920K | 560K
Indiana | 920K | -
Florida | 2M | -
Tennessee1,2 | - | 204K
TOTAL | ~8.6M | ~1.7M

## Slide 3: Duke Energy & Piedmont Natural Gas Customer Transformation Journey
2018
2019
2020
2021
2022
Release Schedule
3
5
8
4
Iterative
Sep
Apr-Jun
Apr
Nov
1
Jun
2
Feb
Customer Engagement
Universal Bill
--------------------------------------------------------------------------------------Duke Energy Core Meter to Cash-----------------------
Early Analytics
DEC
DEF & DEP
DEMW
Apr
6&7
2023/2024
9
---------PNG Meter to Cash--------
Jul 2024
PNG
Duke Energy R5-R8 Key Accomplishments
Largest SAP customer implementation in North America Delivered full scope 5 months ahead of schedule 10.3 million accounts 21 billion records converted Touchless batch billing by Day 3 Converted 300 systems & 1500 interfaces Universal processes across ALL jurisdictions Set new utility benchmarks & applied lessons learned for improvement with each release
Piedmont Natural Gas R9 Key Accomplishments
Separate SAP ISU customer system implementation Delivered full scope 3 months ahead schedule 1.2 million accounts <1 billion records converted Touchless batch billing by Day 3 Converted 60 systems & 230 interfaces Leveraged prior SAP ISU implementation team, development, & materials to accelerate delivery One of the first SAP ISU Greenfield billing implementations using SAP RISE cloud hosting

## Slide 4: The Brutal Truth
70-80% of utility CIS programs fail to hit up to 70% of their promised benefits*
Most Programs don’t fail to meet these benefits purely based on technology – they fail on people, culture, and overall adoption
* - per sources like Gartner, EPRI, and their internal benchmarking

## Slide 5: 3 Fundamental Pillars of CIS Program Success
Methodology, Governance, & Execution
Culture & Adoption
People
People are the foundation for success
Dedicated team members
Deliberate overstaffing of key areas to meet adoption goals
Purposeful Culture and Adoption activities are key to delivery
“One Team” shared accountability across all groups involved
Intentional Organizational Change Management
Clear delivery methodology and milestones with entry & exit criteria
Ongoing weekly status updates with sponsors and stakeholders
Aligned deliverables and impacts across all groups

## Slide 6: The People Factor
Incentives
Poor resource planning and allocation, including non-dedicated teams, is the primary cause of failure for 23% of projects that miss delivery goals.
Overallocated resources make 73% more mistakes than properly allocated ones
Prior Experience
Enables better anticipation and risk management – high performing team with skilled members achieve up to 63% higher success rates
Improves efficiency and decision-making
Boosts alignment, engagement and productivity – up to 37% higher productivity, 65% lower turnover, 22% higher level of loyalty
Dedicated Resources
Retain Talent – Burnt-out or unmotivated staff are 2.5 to 6x more likely to leave
Raises Success
In the world of complex IT Project delivery, the single greatest predictor of success is not the methodology or budget, it is the assembling the right team of dedicated and experienced individuals who own the outcome.

## Slide 7: People & Teams
Dedicated Duke Energy Delivery Team & Management
Consultants: System & Adoption Implementors,
Auditors, Legal
CIS Software Vendor
IT Operations
Customer Operations & Business Process Owners
Internal Impacted Teams (e.g. Finance, Grid Operations)
Impacted Vendors (e.g. Products & Services, Suppliers)
  Form a highly experienced, dedicated “A-Team” with strong business/technical skills & high-level of accountability and delivery expertise
  Ensure tight alignment with Regulatory, Contracts/Supply Chain, and PMO leaders to manage requirements, rate cases, and contracts efficiently.
  Include retention, incentive and overstaffing of Operations teams
Core Duke Energy CIS team
  Experienced teams with past CIS Implementation success
    Leverage experienced external partners including RFI/RFP advisory, named SI core team, and Software vendor and cloud hosting specialists.
    Dedicated Change/Adoption, QA audit teams, and legal support for contract and T&C management.
Consultants/CIS Software Vendor and Hosting
  Engage Business Process Owners and key Customer Operations staff early to shape decisions, validate processes, and support demos.
  Partner proactively with IT Operations to address workstation, infrastructure, networking, and security needs.
Internal Operations
  Dedicated dependency management team with experience in business and application areas
  Establishment of key business area & Points of Contacts across all affected groups
  Establishment of dedicated sub-teams within critical interfacing systems
Internal Non-Customer Areas and App Teams
  Engagement of all Product Owners over external application vendors
  Creation of clear and consistent work statements, shared goals and timelines, and defined quality/resource expectations to ensure successful integration.
External Application Vendors
Notes: Core Duke CIS team
  Bring the ‘A Team’ of Dedicated Experienced personnel (Management & Contributors)
    Existing CIS SME’s business and technical
    Tight Regulatory team engagement on changes and ongoing rate cases
    Experienced Contracts/Supply chain members to work through all the contract needs
    A mix of people who have vision and proven App Delivery & PMO experience
  Retention and Incentives built into the budget and project plans
Consultants/CIS Software Vendor and Hosting
  Experienced teams with past CIS Implementation success
    Independent RFI/RFP consultant to work through initial requirements and scoring
    System Implementor with named/dedicated core team
    Dedicated CIS Package/Application and cloud experts from the Software vendor
    Adoption (Change/Culture) Team
    Delivery Audit Team
    External Legal Counsel to review contracts along with associated Terms & Conditions
Internal Operations
  Identification and naming of Business Process Owners which provide input and review of vision, key decisions, processes, and requirements
  Identifying key individuals on Customer Operations teams to include in analysis and demos for input
  Partnering with IT Operations early to ensure they understand workstation, infrastructure, networking, and security considerations
Internal Non-Customer Areas and App Teams
  Dedicated dependency team with experience in business and application areas with significant process and app integration to the CIS
  Establishment of key business area & Points of Contacts across all affected groups
  Establishment of dedicated sub-teams within critical interfacing applications (e.g. Metering, Service orders, etc) to make changes to work with the new CIS platform
  Planned overstaffing for training and per/post cutover activities
External Application Vendors
  Engagement of all Product Owners over external application vendors
  Creation of Work statements/contracts to spin up dedicated teams with app vendors which are critical for success
  Ensure vendor teams are bringing quality resources

## Slide 8
The Jaws of Culture
Strategic initiatives are often thwarted by an unhealthy culture
Initiatives
Out
In
BEHAVIORS:
dysfunctional operating silos, turf wars, self-interest, resistance to change, blaming/and excuses stress/burnout
LACK OF:
collaboration, openness, trust,
accountability, coaching & feedback, appreciation, healthy environment
Changing customer strategy
Technology transformation
Changes to process, rules, and regulations
New leadership
Lower
Results

## Slide 9: Preparing the business for the solution was just as important as preparing the solution for the business
Culture Training: Shared Accountability & Support, Transparency, Questioning Attitude
Engagement: Sponsors, Steering Committee, Business Process Owners (BPOs)
Engagement
Culture Training
Business Readiness
Day in the Life Sessions
Engagement
Leading the Change for Managers / Supervisors
Change
Onboard Change Ambassadors
Engagement
Business Readiness Kick-offs
Train-the-Trainer
Continuity Planning
Training and Proficiency
Floor Support
Training
Business Readiness
Training
Go-Live
Business Support
DIAGNOSE /
DEFINE
UNFREEZE
REINFORCE
APPLY
MEASURE
To define current
and future state
To shift thinking
and behaviors
To ensure
long-term change
To achieve
business results
To establish
baselines and
monitor progress
Culture
Customer Communications and Change Management
Culture and Adoption
Overstaffing
Onboard Service Representatives
Notes: We leveraged deliberate methodology to build out the change journey
You can see here all the elements we incorporated to create awareness, desire, knowledge, ability and reinforcement, and we’ll dig into each of these in a bit more detail
But you can see that underpinning this entire journey is culture. That was a key focus for us as we navigated OURSELVES and our STAKEHOLDERS through the change journey. If you don’t have a strong program team that’s working as one and focused on the right things, it’s highly unlikely you’ll deliver a successful change experience for your stakeholders.
Transition
Yes, we had a lot of balls in the air, but we were able to juggle them by maintaining a strong focus on culture.

## Slide 10: Governance, Methodology, and Execution
Project Execution and Monitoring
Weekly status reporting along with issues and risk reviews
Clear and measurable deliverables and visual signs of progress reviews
Defined Project Milestone/Phase Entry and Exit Criteria
Deployment Readiness Tracking, including Go-Live success metrics
Clear roles and accountabilities
Well defined escalation processes and proactive risk management
Well Defined and Strong Governance Groups and Processes
Alignment on Methodology, Strategy, Vision, and Goals
Quickly work through Risks and Issues
Commit/Align on Key decisions – Agree to disagree and then commit
Slow down Application and Process Changes as testing starts, freezing changes and transactions approaching deployment
Ongoing Reviews of Competing Initiatives, logging risks and escalating as needed

## Slide 11: Governance Structure
Major schedule shift
Major project dependency priority setting (i.e., IVR replacement vs Customer Connect)
Configuration approach
Migration approach
Environment tuning approach
Program Leadership Team
Strategic
Exec
Sponsors
Solution approach
Test approach
Methodology adjustments
Schedule adjustments
Scope adjustments between releases
Resource allocations
Escalated issues
Cross functional escalations, & prioritization
Scope addition or scope movement that impacts planned ROI
Issue Escalation
Strategic Direction
Key Potential Topics
Significant organizational issues
Organizational design issues
Significant role or headcount changes
Cross project issues
Funding alignment
Major policy decisions
Functional/Technical policy setting
Functional/Technical business direction
Major scope changes
Identify and Close risks and issues
Process options/alternatives
Process design issues
Process design conflicts
Technical approach issues/alternatives
Executive Program Leadership
Business Process Owners
Business SMEs
Industry Advisors
Engagement leads
“Business” includes both functional and technical stakeholders
3rd Party Quality Management services across the program
Program Teams
Data and Analytics
Digital
Choice
Credit & Collections
Customer Service
Device Mgmt
Billing & Rates
Exceptions
Leads & Opportunities
Marketing
Finance & Payments
Products & Services
Service Orders & Outage
Conversion
Example Approvals
Notes: Purpose
  To define the governing framework regarding where decisions are made and the associated roles/accountabilities/escalations in this decision making process to:
    Achieve effective decision making
    Reduce cycle time and costs
    Maintain linkage between the project team and project stakeholders
    Engage and empower employees
Principles
  Ensure the governance model roles are clear and responsibilities are executable
  Empower and concentrate decision making within the core project team. Majority(95+%) of decisions should be made within the core team
  Elevate decisions outside of the core project team only when organizational structures, headcount changes, other projects are materially impacted and/or when there are significant scope, budget or timeline changes
  Push decision making as low as possible within the core team.
  Leverage Business Process Owners (this encompasses business and technology partners) for validation, support, insights/guidance but avoid transferring decision making authority

## Slide 12: Initial Scoping and Due Diligence
Reports show incomplete/poor requirements & major missed software functionality & technology gaps uncovered later are major drivers of project failure, budget overruns, and delays.
  ~200% budget increases along with delayed timelines
Invest upfront in refining scope and selecting the right software and partners to reduce long‑term risks and rework.
  Use demos, proofs of concept, and reference checks to confirm vendor and solution fit.
Define deployment goals and methodology early (multi‑year, phased, or big‑bang) to set clear milestones and success criteria
Current State
Strategy/Vision & Future State
Software Package Fit/Gap
Partner Vendors alignment and experience
Upfront investment and effort to refine scope, choosing the right software and partners for your CIS migration journey pays dividends long term.

## Slide 13: Delivery Methodology
Hybrid Waterfall
Plan
Analyze
Design
Design/Build/Validate
Product
Test
Deploy
Warranty
Functional
Design
Connectivity
Test
Agile Teams
Plan & Analyze
Product
Test
Deploy
Warranty
Build
Test
Design
Iterative Development
Analysis Milestone
Build
Milestone
Test
Milestone
Deployment
Milestone
QI
QI
QI
QI
QI
QI
QI
Regardless of methodologies teams must hit major milestones for deliverables
Overall Program Delivery Methodology – Hybrid Waterfall
Fixed Waterfall Project phases and Milestones, with iterative Design, Build, and component Validation (DBV) in Waves
Phased Release delivery to minimize risk and stagger change impacts
Agile Working Group (AWG’s) bridging the gap between pure Agile teams operating within a hybrid Waterfall model
Operational Readiness Testing
Operational Readiness Testing
QI
Build
Validate
Tech Design
Build
Test
Design

## Slide 14: Dependency Management: Engaging other Agile Teams
Outage AWG
Finance
AWG
1
2
3
Teams
Scrum Of Scrums
Agile Working Groups (AWG’s)
Individual scrum teams established by Dependent Partners to execute delivery work
(Analysis, Design, Build, Test, Training/Change Mgmt, and Deployment)
Dependency Management Steering Committee
CIS Project Leadership
Payment
AWG
1
2
3
Teams
Scrum Of Scrums
Work Mgmt. AWG
1
2
3
Teams
Scrum Of Scrums
Device Mgmt
AWG
1
2
3
Teams
Scrum Of Scrums
1
2
3
Teams
Scrum Of Scrums
1
2
3
Teams
Scrum Of Scrums
1
2
3
Teams
Scrum Of Scrums
Digital Channels AWG
Products & Services AWG

## Slide 15: Ongoing Monitoring & Status Updates
  Weekly
  Status Discussion
  Review Level 1 Issues, Risks, and Key Decisions
  Roundtable
Workstream Alignment
  Weekly
  1-page Status Overview
  Review Level 2 Issues, Risks, and Key Decisions
  Review Key Deliverables
  Roundtable
Sponsor Alignment
  Weekly
  Review Level 3 Issues, Risks, and Key Decisions
  Review Change Requests
  Review Key Deliverables
  Roundtable
Team Leads /Sponsor Alignment
  Weekly
  Executive Status Rollup
  Review Level 3 Issues, Risks, and Key Decisions
  Lookahead Schedule Review & Resourcing
  Roundtable
Executive Leadership Alignment
Program Status Meeting
Key Decisions, Issues, Risk, Scope Review
Workstream Status Reviews
Executive Status Meeting
  Quarterly/As Requested
  Executive Status Rollup
  Regulatory/Legal updates
  Lookahead
  Roundtable
CEO/Board & Regulatory Updates

## Slide 16: Go-Live Readiness Goals and Tracking
Application Readiness
Technical Readiness
Data Readiness
Support Readiness
Business Readiness
Business Readiness
Training Goals met (proficiency)
Communications Plan Complete
Business Activity Freeze implemented
Overall Cut-over plan readiness
Stabilization Metrics defined
Application Readiness
Acceptable defect counts prior to Go-Live
Functional/End to End Testing Exit Criteria Met
Bill comparison complete and match Goals Met with described variances
Technical Readiness
Application and Integrations Response and Performance verified
Critical Batch performance and timing verified
High Availability/Disaster Recovery tested and ready
Data Readiness
Conversion Accuracy/Quality and Timeline goals met
Manual Conversion and fall-out handling defined
Data cleansing activity progress
Support Readiness
Support model/staffing progress
War Room/go-live support model establishment
Knowledge Transfer/Training to support staff progress
System/SLA/KPI monitoring tools in place
Defect Workarounds identified and communicated
Five Key Readiness Categories with associated clear measurable metrics and goals required for Go-Live

## Slide 17: Recap of Differentiators
Transforming Customer Experience Along the Way
Process Reengineering on the
Front End
Automation and Innovation
Elements
Not just a like-for-like CIS
replacement
Separate System Integrator and
OCM Vendors
Dedicated budget, resources and incremental staffing
User proficiency approach to
support ability and reinforcement
Phased delivery to minimize risk
and stagger change impacts
Business and App Change Freezes
Strong Alignment with other Teams
Notes: Outcome must improve Customer Experience (others play defense only)
Defining & implementing universal process - Journey (most do process redesign post go live)
Delivery every year focusing on minimizing risk while staggering change impacts
Expectation for automation and innovation
Not just replacing CIS, implementing a complete Customer Engagement Platform
Separated System Integrator and OCM Vendors (fixed fee SOW’s)
Performance & Sustainability within SOW
ADKAR for Business Readiness
(awareness, desire, knowledge, ability, reinforcement)
Secured funding for Operational impacts including Training and facilities, incremental staff for training and proficiency for all impacted Stakeholders
Capital/O&M split
Regulatory -deferral of O&M at program kickoff
Impacted stakeholders relatively confined to less than 10 sites

## Slide 18
Keeping up with SAP Updates and Planning for the Future
Looking Ahead

## Slide 19: Recently Completed and In-Progress Initiatives
Competed/in-progress Technical Health initiatives
Ongoing SAP ISU S4/Hana / GRC Application & Infrastructure updates and upgrades
SAP ISU S4/Hana Data Archival and Purging
Uplifting integrations from SAP PO/CPI to SAP BTP and Edge Cell Integration
Migration of Hybris Commerce from on-premise platform to SAP Commerce Cloud
Retiring/replacing deprecated Hana Smart Data Streaming replications
Strategic/Potential upcoming Tech Health Initiatives:
Potential value/use cases around SAP Joule (mainly Developer functionality at this time).
Evaluation of Signavio for ongoing process improvement
SAP C4C to C4C Version 2 migration
SAP Solman to Cloud ALM Migration
SAP EnableNow to WalkMe migration
OpenText SaaS Migration

## Slide 20: Customer and Customer Service AI Initiatives
Customer Facing
  Continued IVR agent functionality
  Additional web/self service Chatbot functions (e.g. Explain my bill)
  Increased accuracy for High Usage Alert notifications
Backoffice/Call Center
  Various AI Assistants for Customer Call Representative
  Enhance targeted product and service offerings